[ Cover photo — Paryavaran Sakhis at the Himmatpur Dotiyal facility / Corbett landscape ]

Mitti Se Mitti

A Wet Waste-to-Compost Initiative by the Paryavaran Sakhis of Corbett

Proposal  |  FY 2026–27

Shared by

Waste Warriors Society

www.wastewarriors.org

Submitted to

Eicher Group Foundation

From the Edge of Corbett

A moment in the village

Just beyond the boundary of Corbett Tiger Reserve, morning light filters through the sal trees. Women carry baskets to work. Children leave for school. And every day, a quiet but growing problem festers: organic waste, mixed, dumped, and left to rot.

Hotels and resorts that feed from the tiger reserve's fame generate tonnes of kitchen waste. Households, no longer dependent on livestock, have nowhere to send their wet organic refuse. The rivers that flow through Corbett carry the consequences downstream.

The question before us is simple: Can the communities on Corbett's edge turn this waste back into something that gives — back to the soil, back to the family, back to the forest?

We believe they can.

About Waste Warriors

Waste Warriors Society is a non-profit organisation catalysing systemic change to solve the waste management crisis of the Indian Himalayan Region. Our work lies at the intersection of Climate Change, Biodiversity Habitat Conservation, and Informal Livelihoods through bringing behavioural change in the community. With a team of 240+ Warriors across Uttarakhand and Himachal Pradesh, we focus on enabling better governance, addressing infrastructure and policy gaps, and activating communities to co-create solutions.

| Zero Waste Programs Shimla · Manali · Dharamshala · Corbett and more | 1,200+ Waste Workers Engaged, onboarded, or trained across the region | 13 Years Building waste solutions in the Indian Himalayas |
| --- | --- | --- |

[ Photo — Waste Warriors team / field activity in Corbett or Himachal Pradesh ]

The Waste Crisis at Corbett's Edge

| Corbett Tiger Reserve is home to over 600 species of birds, the Bengal tiger, Asian elephant, and leopard. It is one of India's most ecologically significant landscapes. In recent years, tourism around the reserve has witnessed remarkable growth — bringing livelihoods, but also waste. The increasing volume is driven by booming hospitality, changing rural lifestyles, and rising consumption of packaged goods. Much of this is wet, organic waste — left unmanaged, it rots in the open, leaches into rivers, and draws wildlife towards human settlements, increasing conflict. | [ Photo — waste near village/river ] |
| --- | --- |

≈ 42 metric tonnes of waste generated every single day in the Corbett region — a burden steadily pressing on its forests, rivers, and villages.

According to Waste Warriors' annual waste assessment of the Corbett region. Most of this is unsegregated at source. Without a formal system, wet waste is either dumped in the open, mixed with dry and plastic waste (spoiling recyclables), or burned — releasing toxins in one of India's most sensitive ecosystems.

| 42 MT/day Waste generated in the Corbett region | 600+ Bird species at risk from waste pollution | ~75% Waste unsegregated at source |
| --- | --- | --- |

Our Proven Model: The Paryavaran Sakhis

The Sakhi Initiative

In 2021, Waste Warriors launched the Paryavaran Sakhi model — "friend of the environment" — a community entrepreneurship initiative that addresses the waste crisis through women's empowerment, gender equality, and dignified livelihoods.

Today, 25 women from diverse backgrounds are professional environmental service providers, not passive beneficiaries. They collect, segregate, transport, and process waste — and now, with a wet waste processing facility in place, they are ready to do even more.

| 480 sq. ft. Wet waste processing shed at Himmatpur Dotiyal 400 kg/day Processing capacity of the facility +120 days/month Additional livelihood days for Sakhis through wet waste operations | [ Photo — Paryavaran Sakhis at the wet waste facility ] |
| --- | --- |

"The Sakhis were primarily engaged in dry waste. With the wet waste facility, they can now serve hotels and resorts — creating more consistent, year-round income."

The Project: Mitti Se Mitti

कचरे से खाद, खाद से समृद्धि   ·   From Soil, To Soil

The infrastructure is ready. The Sakhis are trained. What this project funds is the operations, awareness, and systems needed to run the wet waste machine at full scale — and to ensure the communities and businesses around Corbett are part of it.

What we will do — in 3 months

| 🌱 Process 6,000 kg/month Convert wet waste to quality compost at the Himmatpur Dotiyal facility every month. | 👩 Train 6 Paryavaran Sakhis End-to-end training: awareness, collection, transportation, and on-site composting. |
| --- | --- |

| 🏘️ 12 Community Sessions Chai-pe-charcha & focus groups on source segregation and home composting. | 🏨 6 Stakeholder Meetings Engage hotels & resorts to segregate at source and route wet waste to the facility. |
| --- | --- |

| 🪧 Signboards & IEC Direction boards, knowledge-hub signage, home-composting recognition kits for 25 households. | 🌿 Brand the Compost Design a name and identity for the Sakhis' ready-to-use compost — turning waste into a product. |
| --- | --- |

Note on field operations: Reliable waste collection and transportation across the villages and hotels on Corbett's periphery requires a dedicated 4-wheeler vehicle. This is a critical operational need — for both the day-to-day collection runs and to transport processed compost to buyers — and support for the same would go a long way in scaling this initiative.

What Success Looks Like

| 18,000 kg Wet waste processed into compost | 6 Paryavaran Sakhis trained end-to-end | 12 Community awareness sessions | 6 Hotels / resorts onboarded |
| --- | --- | --- | --- |

| 🌍 Environmental | 18,000 kg of wet waste diverted from open dumping — preventing methane, leachate, and wildlife attraction on Corbett's periphery. |
| --- | --- |
| 👩‍💼 Gender & Livelihoods | 6 Sakhis with expanded skills and +120 additional livelihood days per month — growing towards year-round, independent income. |
| 🏘️ Behaviour Change | Measurable improvement in household source segregation across target villages, reinforced by awareness sessions and a home-composting movement. |
| 🏨 Industry Adoption | Hotels and resorts formally onboarded to segregate and route wet waste — a replicable template for the wider hospitality sector. |
| 💰 A New Revenue Stream | Branded, ready-to-use compost sold to nurseries, farmers, and hotels — turning waste into income that outlasts this grant. |

| [ Photo — Wet waste being processed ] | [ Photo — Sakhis at work ] | [ Photo — Corbett landscape / forest ] |
| --- | --- | --- |

Budget and Timeline

Timeline: 3 months, FY 2026–27

| Month 1 | Setup & Mobilise | Sakhi training · Procure consumables & safety gear · Design compost brand · First awareness sessions · Install signboards · Begin processing |
| --- | --- | --- |

| Month 2 | Scale & Engage | Full-scale processing (6,000 kg) · Stakeholder meetings with hotels · Home-composting kits distributed · IEC collateral installed at site |
| --- | --- | --- |

| Month 3 | Consolidate & Sustain | Final awareness rounds · Compost market linkage · Recognise composting households · Documentation & final report |
| --- | --- | --- |

Budget Summary — Total: ₹2,75,420

The estimated budget required for the Mitti Se Mitti project, FY 2026–27, is ₹2,75,420/- (Two Lakh Seventy-Five Thousand Four Hundred and Twenty Only).

| Code | Head / Activity | Target / Frequency | Amount (₹) |
| --- | --- | --- | --- |
| A | Awareness & IEC |  | 1,47,920 |
| A a) | Awareness Sessions (chai-pe-charcha, FGDs, exposure visits) | 12 × ₹660 | 7,920 |
| A b) | Stakeholders' Meet (hotels & resorts) | 6 × ₹5,000 | 30,000 |
| A c) | IEC Collaterals (on-site knowledge hub) | – | 50,000 |
| A d) | Signboards (direction + composting recognition) | 4 × ₹15,000 | 60,000 |
| B | Operations |  | 1,07,500 |
| B a) | Waste Management Consumables (gloves, drums, trolley, earthen pots, guides, certificates, compost brand) | – | 92,500 |
| B b) | Training & Capacity Building of 6 Paryavaran Sakhis | 3 × ₹5,000 | 15,000 |
| C | Office Expenses |  | 20,000 |
| C a) | Printing & Stationery (stakeholder report & office) | – | 10,000 |
| C b) | Local Travel | – | 10,000 |
| TOT | TOTAL |  | 2,75,420 |

WWS Due Diligence

| S.No. | Particulars | Applicable? | Registration Date | Valid Till |
| --- | --- | --- | --- | --- |
| 1 | NGO Registration | Yes | 17-11-2012 | 17-11-2027 |
| 2 | Permanent Account Number | Yes | 17-11-2012 | Perpetual |
| 3 | Certificate under 12A | Yes | 02-03-2026 | 31-03-2036 |
| 4 | Certificate under 80G | Yes | 02-03-2026 | 31-03-2031 |
| 5 | CSR 1 Registration | Yes | 19-04-2021 | Perpetual |
| 6 | FCRA (Renewal Applied) | Yes | 15-11-2017 | 01-04-2028 |
| 7 | Employee Provident Fund (EPF) | Yes | 27-11-2015 | Perpetual |
| 8 | Audited Balance Sheets (last 3 yrs) | Yes | – | – |

Other Donors / Partners of Waste Warriors Society

Parle Biscuits Pvt. Ltd. · Airbnb · MacArthur Foundation · HDFC Bank Ltd · HT Parekh Foundation · Lal Family Foundation · Give India Foundation · Make My Trip Foundation · Rain Matter Foundation · EdelGive Foundation · Rohini Nilekani Philanthropies · Godrej Consumer Products Ltd · SBI Foundation

OUR SINCERE GRATITUDE TO YOU FOR CONSIDERING OUR PROPOSAL

| Mayank Sharma CEO, Waste Warriors Society mayank.sharma@wastewarriors.org | Lehar Arora Manager — Partnerships lehar.arora@wastewarriors.org |
| --- | --- |

Waste Warriors Society (WWS)

Registered under the Societies Registration Act 1860 · Number 243/2012-2013

136/2/2, Shivam Vihar, Jakhan, Rajpur Road, Dehradun, Uttarakhand – 248001

Phone: +91 7505763049  |  Email: partnerships@wastewarriors.org  |  Website: www.wastewarriors.org