Annexure – 1

FORMAT OF PROJECT PROPOSAL FOR GRANT UNDER CSR

| Name of Sponsoring Agency : | National Backward Classes Finance & Development Corporation (NBCFDC) A Govt. of India Undertaking, M/o Social Justice & Empowerment, Govt. of India |
| --- | --- |
| Contact Details : (Name, Phone, Fax, E-mail) | Sh. Ajit Kumar Samal, Senior General Manager (Finance/CS) Phone: 011-45854400 / 9717699911 E-mail: cs@nbcfdc.gov.in |

Part – I:    FORMAT FOR SUBMISSION OF PROJECT PROPOSAL

All the proposals, unless otherwise desired, shall be submitted by the Implementing Agency/District Authorities as per the following format. The project proposal should be as per format in Part I mentioned herein and should be accompanied by the documents as per Part II.

1.  TITLE OF THE PROJECT

The Good Trek Project: Preserving Himalayan Trails Through Responsible Waste Management

2.  CURRENT SOCIO-ECONOMIC STATUS OF THE AREA AND TARGET GROUP

The project is situated in Sankri village, Uttarkashi district, Uttarakhand — the primary gateway to the Kedarkantha Trek, located within the ecologically sensitive Govind Wildlife Sanctuary and National Park. The Indian Himalayan Region (IHR) is home to over 50 million people, of whom approximately 75% reside in rural areas and depend heavily on agriculture, pastoralism, and an increasingly critical tourism economy.

Skill Level of Beneficiaries

| Skill Category | Description / Role |
| --- | --- |
| Skilled | Trek guides with certified training, experienced mule handlers |
| Semi-Skilled | Porters, waste-collection workers, community mobilisers |
| Unskilled | Daily-wage labourers in waste handling, local sorters at drop-off points |

Current Income Level & Gender Profile

Local communities around the Kedarkantha route are predominantly dependent on trekking-season revenues (October–May). Average daily earnings for porters and guides range from ₹400–₹800 per day during peak season, with negligible income during the monsoon closure (June–September). Women remain underrepresented in formal trekking roles; however, Waste Warriors actively promotes dignified livelihood opportunities for women through waste-handling and community engagement roles, consistent with its organisational mandate to ignite urgency among women and youth to earn identity through dignified livelihoods.

Tourism in the region generates over ₹200 crore annually but the burden of unmanaged waste falls disproportionately on local communities — degrading grazing lands, water sources, and village aesthetics — while trekkers return to urban centres unaffected.

3.  OBJECTIVES OF THE PROJECT

1.  Establish a Structured Waste Management System: Create a formal, agency-led system for waste collection, segregation, and transportation along the Kedarkantha Trek route where none previously existed.

2.  Divert Trek Waste from Fragile Ecosystems: Collect and divert a minimum of 6 metric tonnes (MT) of trek-generated solid waste from the high-altitude Himalayan ecosystem over the project period.

3.  Ensure Responsible Processing: Ensure at least 80% of collected waste is properly segregated at source and transported to Waste Warriors' Material Recovery Facility (MRF) in Dehradun for sorting, recovery, and verified recycling.

4.  Engage Trekking Agencies: Formalise collaboration with 45+ trekking agencies operating on the Kedarkantha route, embedding waste responsibility into their operations and guest experience.

5.  Promote Behaviour Change Among Trekkers: Reach a minimum of 5,000 trekkers with targeted behaviour-change communication and responsible-trekking awareness initiatives.

6.  Build a Scalable and Replicable Model: Develop an institutionalised trek-waste management model that can be adopted across other trekking corridors in the Indian Himalayan Region.

7.  Strengthen Local Livelihoods: Create dignified employment opportunities for local community members — particularly women and youth — in waste collection, handling, and awareness activities.

4.  EXECUTIVE SUMMARY OF PROPOSAL

The Indian Himalayan Region (IHR) is one of the world's most ecologically fragile landscapes. Nearly one million trekkers explore mountain trails annually through organised expeditions, generating approximately 288 grams of solid waste per visitor per day. Popular routes such as Kedarkantha, Har Ki Dun, and Valley of Flowers bear the brunt of this growing waste crisis — waste that is burned, buried, or left on slopes in the absence of any formal management system.

Waste Warriors Society (WWS) — a non-profit organisation with 240+ field staff across Uttarakhand and Himachal Pradesh — implemented a successful pilot trek-waste management initiative in Sankri village (December 2025 – February 2026), collecting approximately 2 metric tonnes of trek waste for the first time and transporting it ~200 km to WWS's Material Recovery Facility (MRF) in Dehradun for processing.

Building on this proven pilot, The Good Trek Project seeks CSR support of ₹9,78,650/- (Nine Lakhs Seventy Eight Thousand Six Hundred and Fifty Only) for FY 2026-27 to scale this model into a structured, agency-led waste management system across the Kedarkantha Trek. The project will partner with 45+ trekking agencies, train guides and porters, establish designated waste drop-off points, and engage 5,000+ trekkers in responsible trekking practices — collectively diverting 6+ MT of waste from the Himalayan ecosystem and demonstrating a replicable blueprint for responsible mountain tourism across India.

5.  TARGETED GROUP OF THE PROJECT PROPOSAL

| Target Group | Role / Engagement |
| --- | --- |
| Trekking Agencies (45+) | Registered trekking operators on the Kedarkantha route who will integrate waste management into their operational packages. |
| Trek Guides & Porters | Semi-skilled individuals who lead trekking groups and carry supplies — trained to oversee on-trail waste segregation and collection. |
| Local Community Members | Residents of Sankri and surrounding villages, particularly women and youth, engaged in waste collection, drop-off point management, and awareness activities. |
| Trekkers (5,000+) | Adventure tourists visiting the Kedarkantha route, reached through behaviour-change communication for responsible trekking practices. |
| Local Governing Bodies & Forest Department | Stakeholders from Uttarakhand Forest Department, Gram Panchayats, and tourism boards engaged to institutionalise responsible waste practices. |

6.  GEOGRAPHICAL AREA OF EXECUTION AND REASON FOR SELECTION

Project Area:  Kedarkantha Trek Route — Sankri Village, Uttarkashi District, Uttarakhand. The project corridor spans the trail from the Sankri base camp (approximately 1,920 m) to the Kedarkantha summit (3,810 m), traversing the Govind Wildlife Sanctuary and National Park.

Rationale for Selection

High footfall and acute waste impact: Approximately 20,000 trekkers annually (300–500/day at peak), generating significant solid waste with no prior formal management system.

Existing WWS presence and pilot success: The Sankri pilot (Dec 2025–Feb 2026) already diverted 2 MT of waste, proving feasibility and establishing community trust.

Ecological sensitivity: The route lies within the snow leopard conservation landscape of Govind Wildlife Sanctuary — making responsible waste management a conservation imperative.

Connected to WWS's Dehradun MRF: The established logistics corridor (~200 km) to the Material Recovery Facility in Harrawala, Dehradun, enables responsible downstream processing.

Replication potential: Kedarkantha is a flagship template; success here creates a blueprint for other trekking corridors (Har Ki Dun, Valley of Flowers, Gaumukh Tapovan, etc.).

7.  PROJECT COST

(A)  Budget Details — Detailed Cost Break-Up (Head-wise and Activity-wise)

| Budget Code | Budget Head | Unit Cost (₹) | No. of Units | Annual Budget (₹) |
| --- | --- | --- | --- | --- |
| A | OPERATIONAL EXPENSES |  |  | 2,75,000 |
| A1 | Waste Handling, Transportation & Processing to MRF Dehradun | 20,000 | 5 trips | 1,00,000 |
| A2 | Labour/Mule charges for waste collection | 1,000 | 12 | 12,000 |
| A3 | Community Engagement Activities | 25,000 | 1 | 25,000 |
| A4 | IEC and Project Collaterals | 10,000 | 5 | 50,000 |
| A5 | Transportation / Local Conveyance | 1,000 | 20 | 20,000 |
| A6 | Signboards | 17,000 | 4 | 68,000 |
| B | CAPITAL EXPENSES |  |  | 2,16,000 |
| B1 | Waste Consumables (bags, gloves, litter pickers, safety equipment, weighing machine) | 60 | 1,600 units | 96,000 |
| B2 | Waste Drop-Off Points (infrastructure) | 1,20,000 | 1 | 1,20,000 |
| C | PROJECT TEAM SALARIES |  |  | 3,60,000 |
| C1 | Project Associate | 30,000 | 8 months | 2,40,000 |
| C2 | Project Executive | 15,000 | 8 months | 1,20,000 |
| E | ADMINISTRATIVE EXPENSES (10%) |  |  | 1,27,650 |
|  | TOTAL PROJECT COST |  |  | 9,78,650 |

(B)  Means of Finance of the Project Cost

The total project cost of ₹9,78,650/- (Nine Lakhs Seventy Eight Thousand Six Hundred and Fifty Only) is proposed to be funded entirely through the CSR grant from the sponsoring agency under the NBCFDC CSR framework. Waste Warriors Society shall contribute in-kind through institutional support, field staff oversight, MRF infrastructure access, and established recycling-partner networks at no additional charge to the project.

(C)  Funding Requirements — Phased Disbursement

| Phase | Amount | Purpose |
| --- | --- | --- |
| Start of Project (Month 1–2) | 40% = ₹3,91,460/- | Initial capital expenses (drop-off points, consumables), hiring of project team, agency onboarding, and IEC material development. |
| Mid-Project (Month 3–6) | 40% = ₹3,91,460/- | Operational expenses (transportation trips, mule charges, community engagement), team salaries, and ongoing signage installation. |
| End of Project (Month 7–8) | 20% = ₹1,95,730/- | Final transportation runs, documentation, monitoring and evaluation, recognition event for exemplary agencies, and final report submission. |

Activity-wise Timeline

| Activities | Budget (₹) | Start Date | End Date | No. of Days |
| --- | --- | --- | --- | --- |
| 1. Agency engagement & onboarding; MoU signing with 45+ trekking agencies | 25,000 | Jul 2026 | Aug 2026 | 45 |
| 2. Waste drop-off point construction & installation of signboards | 1,88,000 | Jul 2026 | Sep 2026 | 60 |
| 3. Procurement of waste consumables (kits, bags, equipment) | 96,000 | Aug 2026 | Sep 2026 | 30 |
| 4. Training of guides, porters & local staff; IEC campaigns for trekkers | 1,00,000 | Sep 2026 | Feb 2027 | 150 |
| 5. Trek waste collection, segregation & transportation to MRF (5 trips) | 1,00,000 | Oct 2026 | Feb 2027 | 120 |
| 6. Labour / mule charges for on-trail waste collection | 12,000 | Oct 2026 | Feb 2027 | 120 |
| 7. Community engagement activities & recognition events | 25,000 | Nov 2026 | Feb 2027 | 90 |
| 8. Project team salaries (Project Associate + Project Executive) | 3,60,000 | Jul 2026 | Feb 2027 | 245 |
| 9. Administrative expenses (10%) | 1,27,650 | Jul 2026 | Feb 2027 | 245 |
| TOTAL | 9,78,650 |  |  |  |

8.  EXECUTION / IMPLEMENTATION SCHEDULE

Phase 1 — Mobilisation & Setup  (July – September 2026)

Sign MoUs and onboard 45+ trekking agencies operating on the Kedarkantha route.

Procure and distribute waste collection kits (bags, gloves, litter pickers, weighing machines).

Construct and install waste drop-off points at strategic locations along the trail.

Install informational signboards at key points along the route.

Recruit and induct the project team (Project Associate and Project Executive).

Conduct baseline assessment of waste generation and littering hotspots.

Phase 2 — Operations & Capacity Building  (October 2026 – January 2027)

Conduct structured training workshops for trek guides, porters, and local waste handlers on segregation, safe handling, and responsible disposal.

Deploy IEC (Information, Education, Communication) campaigns targeting trekkers at base camps and trail entry points.

Activate waste collection system across the trail: guides oversee segregation; waste consolidated at drop-off points.

Execute 5 transportation runs to MRF Dehradun (~200 km), ensuring chain-of-custody documentation.

Engage local governing bodies — Gram Panchayat, Forest Department, and Uttarakhand Tourism — for institutional support.

Conduct mule/labour-based collection along sections inaccessible to vehicles.

Phase 3 — Consolidation, Recognition & Reporting  (February 2027)

Complete final transportation run of collected waste to MRF for processing.

Host recognition event for trekking agencies demonstrating exemplary waste management.

Document learnings, scale-up recommendations, and model replication guide.

Submit final project completion report with photographic evidence, weight records, and impact metrics to NBCFDC.

Initiate stakeholder consultations for replication on Har Ki Dun and Valley of Flowers routes.

9.  HUMAN RESOURCES INVOLVED IN PROJECT IMPLEMENTATION

The project will be implemented under the overall stewardship of Waste Warriors Society. A dedicated project team will be deployed on the ground, supported by WWS's existing field infrastructure across Uttarakhand.

| Name / Role | Designation & Responsibility | Contact | Email / Location |
| --- | --- | --- | --- |
| Mayank Sharma | Chief Executive Officer — WWS (Project Oversight & Strategic Direction) | +91-7505763049 | mayank.sharma@wastewarriors.org |
| Lehar Arora | Manager — Partnerships (Donor Liaison & Agency Coordination) | N/A | lehar.arora@wastewarriors.org |
| Project Associate (To be recruited) | On-ground operations management, agency coordination, data collection | To be assigned | WWS Field Office, Sankri/Dehradun |
| Project Executive (To be recruited) | Trekker engagement, IEC delivery, waste collection supervision | To be assigned | WWS Field Office, Sankri |
| Local Trek Guides & Porters (45+) | On-trail waste segregation oversight and responsible collection | Via trekking agencies | Kedarkantha Trail, Sankri |

10.  EXPECTED OUTCOME / BENEFITS OF THE PROJECT

1.  Environmental Impact: Divert a minimum of 6 MT of trek-generated solid waste from the fragile Kedarkantha ecosystem, preventing open burning, dumping, and littering that degrade alpine habitats, contaminate water sources, and harm wildlife.

2.  Waste Processing: Ensure 80%+ of collected waste is properly segregated at source and responsibly processed at the Dehradun MRF — closing the loop from mountain to material recovery.

3.  Industry Adoption: Establish formal, documented waste management protocols with 45+ trekking agencies — embedding environmental stewardship as a standard operating practice, not an afterthought.

4.  Trekker Awareness: Reach 5,000+ trekkers with responsible-trekking behaviour change messaging — creating a generation of mindful mountain travellers.

5.  Livelihood Creation: Generate dignified employment for local community members (especially women and youth) through waste collection, handling, and awareness roles.

6.  Institutional Precedent: Establish the first formal trek-waste management system on the Kedarkantha route — demonstrating to government bodies (Forest Department, Uttarakhand Tourism) and the trekking industry that a viable, scalable model exists.

7.  Scalable Blueprint: Produce a documented replication guide for extending the model to Har Ki Dun, Valley of Flowers, Bali Pass, Kuari Pass, and Gaumukh Tapovan — benefiting the broader Himalayan trekking ecosystem.

11.  MONITORING PLAN OF THE IMPLEMENTING AGENCY

Waste Warriors Society will implement a robust monitoring framework to ensure accountability, track progress against targets, and enable course correction throughout the project lifecycle.

| Monitoring Frequency | Activities & Deliverables |
| --- | --- |
| Monthly | Internal review of waste collected (weight records), transportation trips completed, agency compliance, and trekker engagement figures. Monthly Progress Reports (MPR) submitted to NBCFDC as per the prescribed appendix format. |
| Quarterly | Field visits to the Kedarkantha trail and Sankri base camp by WWS senior staff to audit drop-off point utilisation, segregation quality, and guide/porter adherence. Review of photographic and documentary evidence. |
| Mid-Project (Month 4) | Formal mid-project review: assessment of targets vs. actuals (waste diverted, agencies onboarded, trekkers reached). Identification of gaps and adjustment of operational plan. |
| End of Project (Month 8) | Comprehensive project completion assessment: third-party verification of total waste diverted, MRF processing records, agency participation registers, trekker engagement data, and submission of final report to NBCFDC with full financial utilisation statement. |
| Post-Project (6 months after) | Follow-up monitoring to assess sustainability of the system: whether trekking agencies continue waste practices independently, whether drop-off infrastructure is maintained, and early evidence of replication on other routes. |

12.  SUSTAINABILITY COMMITTEE — POST-HANDOVER

To ensure the long-term sustainability of the waste management system beyond the CSR project period, a Trek Waste Management Committee will be constituted, composed primarily of community representatives and institutional stakeholders who will eventually take ownership of the system.

◆  Village-Level Representative
(Gram Panchayat, Sankri): Elected local leader who will liaise with trekking agencies, oversee drop-off point maintenance, and coordinate with district waste management authorities.

◆  Forest Department Representative
(Govind Wildlife Sanctuary): Ensures ongoing compliance with environmental norms and facilitates access to sanctuary areas for waste collection activities.

◆  Trekking Agency Consortium Lead
(rotating, from 45+ partners): Represents the trekking industry; drives voluntary compliance, peer accountability, and collective adoption of responsible waste standards.

◆  WWS Field Coordinator
(transition support for 6 months): Provides technical handholding to the committee during transition, ensuring knowledge transfer and system continuity.

◆  Local Youth / Women's Group Representative: Representatives of community groups employed in waste collection roles, ensuring livelihood continuity and local ownership of the programme.

13.  COORDINATOR FOR THIS PROJECT

The following officer of Waste Warriors Society is the designated Project Coordinator, authorised to liaise with NBCFDC on all matters pertaining to this project:

| Name | Mayank Sharma |
| --- | --- |
| Designation | Chief Executive Officer |
| Organisation | Waste Warriors Society |
| Office Address | 136/2/2, Shivam Vihar, Jakhan, Rajpur Road, Dehradun, Uttarakhand – 248001 |
| Phone / Mobile | +91-7505763049 |
| Email ID | mayank.sharma@wastewarriors.org |

Secondary Contact (Partnerships):

| Name | Lehar Arora |
| --- | --- |
| Designation | Manager — Partnerships |
| Email ID | lehar.arora@wastewarriors.org |

Part – II:    LIST OF ANNEXURES TO PROJECT PROPOSAL

1.  Undertaking by the Implementing Agency
     Waste Warriors Society will execute an undertaking on its official letterhead stating that it will abide by all terms and conditions of the CSR grant; will not divert funds or entrust execution to other organisations (unless agreed by NBCFDC in writing); and accepts full liability for refund of entire/unutilised grant amounts in the event of any breach.

2.  Copy of Registration Certificate / Trust Deed / MOA
     WWS is registered under the Societies Registration Act 1860 — Registration Number 243/2012-2013. Copy enclosed.

3.  Annual Reports with Audited Accounts (Last 3 Years)
     Audited financial statements for the past three years with auditor's reports — to be enclosed.

4.  PAN Card and TAN Number
     Copy of PAN Card and TAN Number — to be enclosed.

5.  List of Board of Directors / Executive Committee Members
     List with addresses and contact numbers — to be enclosed.

6.  List of Major Donors / Partners
     Parle Biscuits Pvt. Ltd., Airbnb, MacArthur Foundation, HDFC Bank Ltd, HT Parekh Foundation, Give India Foundation, Make My Trip Foundation, Rain Matter Foundation, Edelgive Foundation, Rohini Nilekani Philanthropies, Godrej Consumer Products Ltd, SBI Foundation, and others.

7.  Due Diligence Summary
     Refer to the WWS Due Diligence table reproduced below.

8.  Any Other Document
     As may be required by NBCFDC.

WWS Due Diligence Summary

| S.No. | Particulars | Applicable | Registration Date | Valid Till |
| --- | --- | --- | --- | --- |
| 1 | NGO Registration | Yes | 17-11-2012 | 17-11-2027 |
| 2 | Permanent Account Number (PAN) | Yes | 17-11-2012 | Perpetual |
| 3 | Certificate under 12A | Yes | 02-03-2026 | 31-03-2036 |
| 4 | Certificate under 80G | Yes | 02-03-2026 | 31-03-2031 |
| 5 | CSR-1 Registration | Yes | 19-04-2021 | Perpetual |
| 6 | FCRA Renewal Application | Yes | 15-11-2017 | 01-04-2028 |
| 7 | Employee Provident Fund (EPF) | Yes | 27-11-2015 | Perpetual |
| 8 | Audited Balance Sheets (last 3 years) | Yes | — | — |

Name & Signature of Authorised Signatory
Mayank Sharma — Chief Executive Officer
Waste Warriors Society
136/2/2, Shivam Vihar, Jakhan, Rajpur Road,
Dehradun, Uttarakhand – 248001
Phone: +91-7505763049
Email: partnerships@wastewarriors.org
Website: www.wastewarriors.org

All documents (each page) shall be duly signed and stamped by the applicant and the Head of the Grantee Organisation. The Institution shall produce original documents on demand by NBCFDC. The Institution will submit Monthly Progress Reports (MPR) as per the Appendix format enclosed with this proposal.