| IEC & Community Mobilisation Programme Dharamshala, Himachal Pradesh · FY 2026–27 | Waste Warriors Society In partnership with Dharamshala Municipal Corporation |
| --- | --- |

What We Are Doing To make Dharamshala visibly cleaner and improve the Urban Local Body's (ULB / Nagar Palika) Swachhata Survekshan Ranking, Waste Warriors is executing a suite of direct-action interventions and city-wide Information, Education and Communication (IEC) activities — in active partnership with the Dharamshala Municipal Corporation.

| 01 | Regular Follow-ups with 27 Waste Collection Vehicles & Workers — 17 Wards | Daily route monitoring across all 17 wards, verifying segregation compliance and worker accountability at point of collection. |
| --- | --- | --- |
| 02 | Monthly Progress & Knowledge Transfer to the ULB | The team shares IEC, BCC and monitoring progress with the Urban Local Body every month — building institutional capacity and easing the responsibility handover process. |
| 03 | Citizen Feedback Mechanism for Swachhata Activities | Identifying and deploying an easy-to-use mechanism for citizens to give feedback on Swachhata activities directly to the ULB, creating a democratic accountability loop. |
| 04 | Felicitation of Swachhata Champions & Changemakers | Celebrating active citizens, influencers and changemakers of Swachhata initiatives in the project area — building peer recognition and sustaining community momentum. |
| 05 | Signboards, Wall Murals & Art Installations | Messaging designed and submitted to the ULB for formal approval before installation — every high-footfall point becomes a permanent visual anchor of civic responsibility. |
| 06 | Two Zero Waste Melas with Dharamshala Municipal Corporation | City-wide events combining waste awareness, community celebration and felicitation of changemakers — organised in partnership with the DMC. |
| 07 | Monthly Cleanup Drive in Every Ward | A ward-level cleanup drive every month — removing accumulated waste from public spaces and creating a civic platform for youth and women as environmental actors. |
| 08 | Dark Spot Identification, Digital Documentation & Reporting to DMC | Every ward's dumping dark spots identified, digitally mapped and formally reported to the Dharamshala Municipal Corporation — creating an official, actionable waste geography record. |
| 09 | Transformation of 17 Dark Spots (1 per Ward) | Each identified dark spot is physically cleared and converted into a clean, mural-marked public space — removing the physical norm of dumping removes the social norm. |
| 10 | Human Resource Deployment for Smooth Operations | Deploying community mobilisers, field executives and Swachhata Coordinators at ward level throughout the 12-month programme for seamless, continuous delivery. |

| 17 Wards Active Coverage | 27 Vehicles Monitored Daily | 17 Dark Spots Transformed (1/Ward) |
| --- | --- | --- |